## Instructions
Instructions For Completing This Document
Complete the Project Name and Superviser Name
ID: A unique ID number used to identify the requirement
Functional Requirement: This column should be populated with a description of the functional requirement.
Status: This column should be populated with the current status of the functional requirement.
Deadline: This column should be populated for the requirements whose status is incomplete.
Resource: Team member who completed/will complete the requirement implmentation.

## Functional
Project Name: Catalogued
Superviser Name: Sir Aamir Wali
Deliverable: 1
ID | Functional Requirement | Priority | Status Completed | Deadline (week no of semester) | Resource
1 | System should save the Images data from video/images of the employees/students/subjects | 1 | 100% |  | Adeel Shaukat, Bilal Anees, Hira Rauf, Masroor Hussain
2 | System should train on the image data and make a model | 1 | 100% |  | Adeel Shaukat, Bilal Anees, Hira Rauf, Masroor Hussain
3 | System shall do face recognition of multiple persons in the video using the model | 1 | 100% |  | Adeel Shaukat, Bilal Anees, Hira Rauf, Masroor Hussain
4 | System shall do face recognition based on the name/ID/Lable given by operator/user/administrator | 1 | 100% |  | Adeel Shaukat, Bilal Anees, Hira Rauf, Masroor Hussain
5 | System should organize the underlying filesystem so that the video, training data and models can be saved and retrieved accurately | 1 | 100% |  | Adeel Shaukat, Bilal Anees, Hira Rauf, Masroor Hussain
6 | System should get the video chunks of a person from single saved video based on user input | 1 | 70% | 3rd Week | Adeel Shaukat, Masroor Hussain
7 | System should merge all the videos chunks from single video based on user input | 1 | 50% | 5th Week | Masroor Hussain, Adeel Shaukat
8 | System should get video chunks of a person from multiple saved videos based on user input | 1 | 25% | 6th Week | Adeel Shaukat Hira Rauf, Masroor Hussain
9 | System should do chronological sorting of video chunks retrieved from multiple saved videos to make a single video | 1 | 35% | 6th Week | Masroor Hussain, Bilal Anees
10 | System should get video chunks of a person from single live camera | 1 | 100% |  | Adeel Shaukat, Bilal Anees, Hira Rauf, Masroor Hussain
11 | System should merge all the video chunks from single live camera | 1 | 50% | 6th Week | Adeel Shaukat, Hira Rauf, Masroor Hussain
12 | System should perform chronological sorting of videos chunks retrieved from multiple live cameras to make a single video | 1 | 20% | 8th Week | Adeel Shaukat, Bilal Anees, Hira Rauf, Masroor Hussain
13 | System should allow the administrator to provide images and videos for a new model | 1 | 100% |  | Adeel Shaukat, Bilal Anees, Hira Rauf, Masroor Hussain
14 | System should allow the administrator to train the model on provided data | 1 | 100% |  | Adeel Shaukat, Bilal Anees, Hira Rauf, Masroor Hussain
15 | System shall allow the administrator to delete a model | 1 | 100% |  | Adeel Shaukat, Bilal Anees, Hira Rauf, Masroor Hussain
16 | System shall allow the administrator to generate video of a person whose model exists in the system | 1 | 100% |  | Adeel Shaukat, Bilal Anees, Hira Rauf, Masroor Hussain
17 | System should udate the model if new images are added | 2 | 20% | 10th Week | Adeel Shaukat, Masroor Hussain
18 | System shall have graphical user interface so that non-technical user can run the program | 2 | 0% | 9th Week | Bilal Anees, Hira Rauf, Masroor Hussain
19 | System should track the person if he/she is recognized and after that the face is not visible | 2 | 0% | 8th Week | Adeel Shaukat, Hira Rauf
20 | System should get the video from saved/live video where two or more persons appear on the screen at same time based on user's input | 2 | 0% | 10th Week | Adeel Shaukat, Bilal Anees, Hira Rauf, Masroor Hussain
21 | System should merge multiple videos from multiple saved videos | 2 | 20% | 8th Week | Adeel Shaukat, Masroor Hussain
22 | System should get video chunks of a person from multiple live cameras | 2 | 20% | 9th Week | Adeel Shaukat, Bilal Anees
23 | System should merge videos chunks retrieved from multiple live cameras to make a single video | 2 | 0% | 10th Week | Adeel Shaukat, Masroor Hussain
24 | System should allow the administrator to log in using username and password | 2 | 0% | 11th Week | Adeel Shaukat, Bilal Anees, Hira Rauf, Masroor Hussain
25 | System should allow the administrator to log out | 2 | 0% | 11th Week | Bilal Anees, Hira Rauf
26 | System should allow the administrator to name a model | 2 | 100% |  | Adeel Shaukat, Bilal Anees, Hira Rauf, Masroor Hussain
27 | System shall allow only the administrator to update an existing model | 2 | 50% | 11th Week | Adeel Shaukat, Bilal Anees, Masroor Hussain
28 | System shall not allow both the users of this system(General user and Administrator) to use it at the same time. | 2 | 0% | 12th Week | Adeel Shaukat, Bilal Anees, Hira Rauf, Masroor Hussain
29 | System should allow only the authorized users to use this system | 2 | 0% | 12th Week | Bilal Anees, Hira Rauf, Masroor Hussain
30 | System should delete a model with administrator access | 3 | 45% | 13th Week | Bilal Anees, Hira Rauf, Masroor Hussain
31 | System shall use server to host all the training data, model and saved videos | 3 | 0% | 12th Week | Adeel Shaukat, Bilal Anees, Hira Rauf, Masroor Hussain
32 | System shall use Hadoop or spark to increase the efficiency of the program | 3 | 0% | 13th Week | Adeel Shaukat, Bilal Anees, Hira Rauf, Masroor Hussain
|  | 3 | 0% | 16th Week | Adeel Shaukat, Bilal Anees, Hira Rauf, Masroor Hussain
╝

## Non-Functional Requirements
Project Name: Catalogued
Superviser Name: Sir Aamir Wali
Deliverable: 1
ID | Non-Functional Requirement | Priority | Status Completed | Deadline (week no of semester) | Resource
1 | System's interface is convenient to learn and use. | 1 | 75% |  | Adeel Shaukat, Bilal Anees, Hira Rauf, Masroor Hussain
2 | System shall be efficient with minimum training time for a model. | 1 | 50% |  | Adeel Shaukat, Bilal Anees, Hira Rauf, Masroor Hussain
3 | System shall be used by one type of user at a time. | 1 | 50% |  | Adeel Shaukat, Bilal Anees, Hira Rauf, Masroor Hussain
4 | System shall validate the users in such a way that it asks to refill the incorrect field. | 1 | 30% |  | Adeel Shaukat, Bilal Anees, Hira Rauf, Masroor Hussain
5 | System shall sufficiently store hundreds of records in filesystem/storage. | 1 | 70% |  | Adeel Shaukat, Bilal Anees, Hira Rauf, Masroor Hussain
6 | System shall provide maximum accuracy in face recognition. | 1 | 70% |  | Adeel Shaukat, Bilal Anees, Hira Rauf, Masroor Hussain
7 | System shall be available 100% of the time. | 1 | 0% |  | Adeel Shaukat, Bilal Anees, Hira Rauf, Masroor Hussain
8 | System shall be modular enough to add any new functionality in it. | 1 | 60% |  | Adeel Shaukat, Bilal Anees, Hira Rauf, Masroor Hussain
9 | Enhanced efficiency and accuracy of the system | 1 | 40% |  | Adeel Shaukat, Bilal Anees, Hira Rauf, Masroor Hussain
10 | System shall be provided in a package to alleviate user from installing openCV, Python and all environment libraries to run program | 2 | 0% | 10th Week | Adeel Shaukat, Bilal Anees, Hira Rauf, Masroor Hussain
11 | Constraints should be applied to ensure data integrity | 1 | 30% |  | Adeel Shaukat, Bilal Anees, Hira Rauf, Masroor Hussain